## Sheet1
Ochilview Housing Association
Estate Inspections 2020-21
Summary by Area
Month | Planned | Actual | Target | % Completed
2020-04-01 | 10 | 0 | 10 | 0%
2020-05-01 | 11 | 0 | 11 | 0%
2020-06-01 | 10 | 0 | 10 | 0%
2020-07-01 | 18 | 18 | 18 | 100%
2020-08-01 | 10 |  | 10 | 0%
2020-09-01 | 11 |  | 11 | 0%
2020-10-01 | 10 |  | 10 | 0%
2020-11-01 | 18 |  | 18 | 0%
2020-12-01 | 10 |  | 10 | 0%
2021-01-01 | 11 |  | 11 | 0%
2021-02-01 | 10 |  | 10 | 0%
2021-03-01 | 18 |  | 18 | 0%
| 147 | 18 | 147 | 12.24%
Issues by Area
Area | Surveyed | Issues found |  | Action taken
Ash Grove, Alloa | 2020-07-01 | Some debris/rubbish left in common areas |  | Works order issued for removal.
|  | Top and bottom shrub beds require planting. |  | Will obtain quotes for this. May progress at a later stage.
Bank Street, Alloa | 2020-07-01 | Some debris/dumped items at base of stairs to block containing no. 6 |  | Passed to Housing to liaise with tenant for removal.
Bedford Place, Alloa | 2020-07-01 | No issues to report
Bowhouse Gardens, Alloa | 2020-07-01 | Various items of debris/rubbish left in development, particularly at bin stores. |  | Passed to Housing to liaise with tenants for removal.
|  | Some shrub beds require weeding. |  | Passed to landscape contractors to attend to at next site visit.
|  | Bin store door fallen off at no.36 |  | Works order to be issued for repair.
Bridge Terrace, Alloa | 2020-07-01 | Some debris/rubbish left in top bin store area. |  | Passed to Housing to liaise with tenants for removal.
Broad Street/Stripehead, Alloa | 2020-07-01 | No issues at either development.
Burgh Mews, Alloa | 2020-07-01 | No issues to report
Burleigh Way, Alloa | 2020-07-01 | Various items of debris/rubbish left throughout development. |  | Passed to Housing to liaise with tenants for removal.
|  | Bare shrub beds to front of blocks 7-12 and 13-16. |  | Will obtain quotes for this. May progress at a later stage.
Carpenters Wynd, Alloa | 2020-07-01 | No issues to report
Colville Gardens, Alloa | 2020-07-01 | Bin store lock needs repaired |  | Works order issued for repair.
|  | Shrubs and ivy to side of block 85-91 overgrowing. |  | Will obtain quotes for this. May progress at a later stage.
|  | Area to rear of bin store has various weeds growing. |  | Passed to landscape contractors to attend to at next site visit.
Earl of Mar Court, Alloa | 2020-07-01 | Trellis in drying area to 1-6 requires repairs. |  | Works order issued for repair.
Garvalley Crescent & Moir Street, Alloa | 2020-07-01 | No issues to report
Hill Park/Street, Alloa | 2020-07-01 | Some debris/rubbish left in bin store of block 22-32. |  | Passed to Housing to liaise with tenant for removal.
|  | Tree in Car Park requires to be taken down |  | Will obtain quotes for this. May progress at a later stage.
|  | Washing pole drying area @ 46 needs replaced |  | Works order issued for repair.
|  | Window cleaning not to an acceptable standard. |  | Passed to window cleaners for remedial action.
|  | Shrub height needs taken down again. |  | Passed to landscape contractor for trimming back.
Kirkgate, Alloa | 2020-07-01 | Pigeon droppings at front and rear of block 1-11. |  | Works order issued to clear this.
|  | Stair cleaning sheets not updated; window cleaning standard not acceptable. |  | Passed to window cleaners for remedial action.
Mar Street, Alloa | 2020-07-01 | No issues to report. Properties now under re-development so will not be inspected until further notice.
Mercat Wynd, Alloa | 2020-07-01 | No issues to report
Mill Road, Alloa | 2020-07-01 | Debris/rubbish left throughout both blocks (both internally in stairwells and externally). |  | Passed to Housing to liaise with tenants for removal.
|  | Gutter leaking above door 27-29 in odd block. |  | Works order issued for repair
|  | First 4 lights as you enter the block are not working (even side) |  | Works order issued for repair
|  | Closes to 24-26 & 12-14 need repainting / plastering after water ingress. |  | Works order issued for repair
Paton Court, Alloa | 2020-07-01 | Gutter end leaking outside numbers 17-20 |  | Works order issued for repair.
|  | Debris/rubbish left throughout development |  | Some items already awaiting uplift and Housing aware. For others, passed to Housing to liaise with tenants for removal.
St Mungo's Wynd, Alloa | 2020-07-01 | Some debris/rubbish left throughout development. |  | Passed to Housing to liaise with tenants for removal.
|  | Area to rear 30-33 needs cleared of ivy etc. |  | Will obtain quotes for this. May progress at a later stage.
|  | Overflow to no. 26 is leaking. |  | Works order issued for repair.